## Budget Ref (hidden)
Main Categories
Administration
Capacity Building
Staffing
Project Expenses
| Sub-Categories | Main Categories
| Administrative Support Costs (OM) | Administration
| Capacity Building | Capacity Building
| Full Time Staff (35 hours or more per week) | Staffing
| Part Time Staff (less than 35 hours per week) | Staffing
| Transportation | Project Expenses
| Space | Project Expenses
| Honorarium (for participants, volunteers) | Project Expenses
| Support Services (translation, interpretation, child-minding) | Project Expenses
| Project Supplies and Materials | Project Expenses
| Project Equipment (rental or purchase) | Project Expenses
| Food | Project Expenses
| Fees (for services delivered) | Project Expenses
| Contingency | Project Expenses
| Other | Project Expenses

## Project Plan Example
The column titles for this worksheet are in row 2. They span cells A2 inclusive. The following cells have Comments: none. The data spans cells A3 through H24. There is information in every cell for columns A through H. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
Project Plan Example
Check one only. Year 1 Year 2 Year 3 Year 4 | Select the type of activity from the list below: - Project Planning ¦ Prep Time - Recruitment ¦ Outreach - Resource Development - Training (Staff ¦ Volunteers) - Group Workshops ¦ Sessions - Drop in Time - Group Mentoring ¦ Coaching - Individual mentoring ¦ Coaching - Event ¦ Gathering - Ceremony - Partnership ¦ Networking - Doesn't Fit a Category |  |  |  |  | Check resources that apply to the activity in this row. Transportation Space Food Honorarium Support services (translation, child-minding, interpretation etc.) Staff Time Promotional Materials Volunteer Time Project Supplies Equipment Other _____
YEAR | CATEGORY | WHAT ARE YOUR MAJOR ACTIVITIES? | WHEN WILL THE ACTIVITY TAKE PLACE? | WHAT IS THE FREQUENCY OF ACTIVITIES? | HOW MANY PEOPLE? | RESOURCES | OTHER RESOURCES
In which year(s) will your activity take place? | Select the Type of Activity | List the major activities in your project. Use one row per activity. Include things you will do to get ready to deliver your project. Example: Design curriculum. Include activities you will deliver for your parents, guardians and/or caregivers. Example: Deliver workshops. List activities in the order they will occur. | What month(s) of the year will this activity take place? | How often will the activity take place in a one year period? For example: weekly, monthly, once a year etc. | How many parents, guardians and/or caregivers do you expect will participate in this activity? | Select the resources needed to complete this activity. | Add any notes or details about required resources that will help you to build the budget.
1 | Recruitment/Outreach | Outreach to parents, caregivers and guardians across Brampton (all are Afro-Diasporic) Going to start with the organizations we know in our communities. | August - September | 2 days per week during this period. | Not applicable | Promotional Materials Staff Time | Updated Partner List Project Background Info Project Coordinator to lead
1 | Resource Development | Design curriculum for parent and family support program. In year 1, do a needs assessment, build a plan for the weekly sessions (topics, speakers, we will use etc.) | August - October | Not applicable | Not applicable | Staff Time Volunteer Time | Examples of other resources/curriculum
1 | Group workshops/sessions | Group Workshop Activity: Deliver parent and family meet-ups. We want to integrate food, learning and informal discussion into the format of the sessions. We will share a meal together. | October - March | Twice a month week. Total 12 gatherings. | 10-15 women and their kids | Space Food Transportation Child-minding Honorarium Project Supplies | Notebooks, pens, handouts Guest speakers
1 | Group Mentoring/Support | Group Mentoring: neighbourhood parent support groups will meet on their own as well and support each other as needed with childcare, appointments, advice, and neighbourhood resources. | October - May | Minimum once per month until May and as needed afterwards | 10-15 families | Staff time StaffTransportation | Journals for each parent Coffee gift card for parents
1 | Event ¦ Gathering | Annual Holiday Celebration (Year-end celebration) | December | Once per year | 30 | Space Food Transportation Equipment Project Supplies / decorations | Art supplies MC Sound System DJ Holiday cards
1 | Recruitment/Outreach | Reach out to more community groups and research additional community partners, guest speakers | June - July | two meetings per week | Not applicable | Staff time StaffTransportation Promotional materials | Updated Partner List Project Background Info Project Coordinator to lead
2 | Recruitment/Outreach | Outreach to parents, caregivers and guardians across Brampton (all are Afro-Diasporic) Going to try and reach new neighbourhoods we haven't been active in before. | August - September | 2 days per week during this period. | 10 | Promotional Materials Staff Time | Updated Partner List Project Background Info Project Coordinator to lead
2 | Resource Development | Refine and revise curriculum for parent and family support program based on feedback from Year 1 and also with information from a needs assessment of new families, build a plan for the weekly sessions (topics, speakers, we will use etc.) | June - August | Not applicable | Not applicable | Staff Time Volunteer Time | Examples of other program curriculum or workshop formats
2 | Group Workshops/sessions | Group Workshop Activity: Deliver parent and family meet-ups. We want to integrate food, learning and informal discussion into the format of the sessions. We will share a meal together. | October - May | Twice a month week. Total 12 gatherings. | 10-15 women and their kids | Space Food Transportation Child-minding Honorarium Project Supplies | Notebooks, pens, handouts Guest speakers
2 | Group Mentoring/Support | Group Mentoring: neighbourhood parent support groups will meet on their own as well and support each other as needed with childcare, appointments, advice, and neighbourhood resources. | October - May | Minimum once per month until May and as needed afterwards | 10-15 families | Transportation | Journals for each mentee Coffee gift card for each mentee
2 | Event ¦ Gathering | Annual Holiday Celebration (Year-end celebration) | December | Once per year | 30 | Space Food Transportation Equipment Project Supplies | Art supplies MC Sound System DJ Holiday cards
2 | Recruitment/Outreach | Reach out to more community groups and research additional community partners, guest speakers | June - July | Not applicable | Not applicable | Staff time StaffTransportation Promotional materials | Updated Partner List Project Background Info Project Coordinator to lead
3 | Recruitment/Outreach | Outreach to parents, caregivers and guardians across Brampton (all are Afro-Diasporic) Going to try and reach new neighbourhoods we haven't been active in before. | August - September | 2 days per week during this period. | 10 | Promotional Materials Staff Time | Updated Partner List Project Background Info Project Coordinator to lead
3 | Resource Development | Refine and revise curriculum for parent and family support program based on feedback from Year 1 and also with information from a needs assessment of new families, build a plan for the weekly sessions (topics, speakers, we will use etc.) | June - August | Not applicable | Not applicable | Staff Time Volunteer Time | Examples of other program curriculum or workshop formats
3 | Group Workshops/sessions | Group Workshop Activity: Deliver parent and family meet-ups. We want to integrate food, learning and informal discussion into the format of the sessions. We will share a meal together. | October - May | Twice a month week. Total 12 gatherings. | 10-15 women and their kids | Space Food Transportation Child-minding Honorarium Project Supplies | Notebooks, pens, handouts Guest speakers
3 | Group Mentoring/Support | Group Mentoring: neighbourhood parent support groups will meet on their own as well and support each other as needed with childcare, appointments, advice, and neighbourhood resources. | October - May | Minimum once per month until May and as needed afterwards | 10-15 families | Transportation | Journals for each mentee Coffee gift card for each mentee
3 | Event ¦ Gathering | Annual Holiday Celebration (Year-end celebration) | December | Once per year | 30 | Space Food Transportation Equipment Project Supplies | Art supplies MC Sound System DJ Holiday cards
3 | Resource Development | Produce a final resource/parents' guide that features tips, contacts and tools for families. | April - February | Once in final year | 10 parents/guardians or caregivers | Staff Time Printing Honorarium | Updated Partner List Project Background Info Project Coordinator to lead
3 | Event ¦ Gathering | Invite all the families that have participated in the program for a release of the parents guide and invite community partners | May | Once in final year | 35 families | Space Food Transportation Equipment | MC Sound System

## Budget Example
The column titles for this worksheet are in row 2. They span cells A2 inclusive. The following cells have Comments: none. The data spans cells A4 through I29. There is information in every cell for columns A through I. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
Budget Worksheet Example
Complete the detailed budget request below. Use your Project Plan as a guide and try to capture all the expenses you will need.
| Select a category from the list: - Administration - Capacity Building (optional) - Staffing - Project Expenses | Choose an expense item from the list for the selected budget category: If "Administration" selected, choose from: - Administrative Support Costs (OM) If "Staffing" selected, choose from: - Full Time Staff (35 hours or more per week) - Part Time Staff (less than 35 hours per week) If "Project Expenses" selected, choose from: - Contingency - Transportation - Space - Honorarium (participants, volunteers) - Support Services (translation, interpretation, child-minding) - Project Supplies and Materials - Project Equipment (rental or purchase) - Food - Fees (for services delivered) - Other (specify in "Budget Notes") | Use this column to share more details or calculations about the expense on this line
| Budget Category | Expense Item | Budget Notes Use this space to show us how you calculated the amounts you are requesting. | Request Amount Year 1 | Request Amount Year 2 | Request Amount Year 3 | Request Amount Year 4 | TOTAL
Required | Administrative | Administrative Support Costs (OM) | Formula: maximum 15% of your total annual budget. | 10560 | 10560 | 9882.75 |  | 31100
Optional | Capacity Building | Capacity Building | $4000 maximum per year | 4000 | 4000 | 4000 |  | 12000
| Staffing | Part-Time Staff | $22 per hour x 30 hours x 52 weeks * 1.2 (Mandatory Employment Related Costs) | 41184 | 41184 | 41184 |  | 123600
| Staffing | Part-Time Staff | $22 per hour x 10 hours x 30 weeks * 1.2 (Mandatory Employment Related Costs) | 7920 | 7920 | 7920 |  | 23800
| Project Expenses | Project Supplies and Materials | Design and print flyers for outreach to families and community partners | 250 | 250 | 250 |  | 800
| Project Expenses | Transportation | Staff and facilitator transportation for meetings, outreach etc. | 250 | 250 | 250 |  | 800
| Project Expenses | Transportation | For participants: 12 meetings x 15 families (round trip) | 1980 | 1980 | 1980 |  | 6000
| Project Expenses | Space | Monthly meeting space and training space = $150 per meeting x 12 meetings | 1200 | 1200 | 1200 |  | 3600
| Project Expenses | Supplies | Childminder's honorariums and supplies for bi-monthly meet ups. About $150 per monthly session. | 1800 | 1800 | 1800 |  | 5400
| Project Expenses | Project Supplies and Materials | Need coffee cards for neighbourhood support meetings valued at $20 (15 parents x $20 per card). See project worksheet for more details. | 300 | 300 | 300 |  | 900
| Project Expenses | Food | Bi-monthly meetings. $6 per person x 30 parents and kids + 3 staff/facilitators | 2376 | 2376 | 2376 |  | 7200
| Project Expenses | Food | Annual celebration event $15 per person X 35 people | 525 | 525 | 525 |  | 1600
| Project Expenses | Space | Rental space for annual celebration | 200 | 200 | 200 |  | 600
| Project Expenses | Fees (for services delivered) | Fees for Celebration Event - DJ and MC | 500 | 500 | 500 |  | 1500
| Project Expenses | Equipment (rental or purchase) | Rent sound system for celebration event | 200 | 200 | 200 |  | 600
| Project Expenses | Space | Closing Event and Resource handbook release | 800 | 800 | 800 |  | 2400
| Project Expenses | Honorarium | 1 guest facilitator for every session ($100 x 12) | 800 | 800 | 800 |  | 2400
| Project Expenses | Printing | Printing of resource handbook, one copy per family |  |  | 800 |  | 800
| Project Expenses | Equipment (rental or purchase) | Rent projector and screen and sound system |  |  | 800 |  | 800
| Project Expenses | Contingency | up to 10% of your total annual budget | 5632 | 5632 |  |  | 11300
| TOTAL YOF BUDGET REQUEST |  |  | 80477 | 80477 | 75767.75 | 0 | 237200
TIP! Watch your annual funding ceiling. Family Innovations Scale the ceiling is $125,000 per year Family Innovations Test the ceiling is $85,000 per year